## Defect Tracking Log
DEFECT TRACKING LOG
Project Name | Calculator.net & GameBanana
Program Manager
Project Manager
Purpose: To ensure that the work product meets specifications for performance, defects must be tracked and fixed. These defects may arise from any Phase, but the majority will arise in the Testing Phase and must be properly captured and tracked through resolution. This form will allow documentation of test defects that must be corrected prior to project completion. Also, this form makes it easier to monitor status of the defect correction progress. This form may be used by any member of the software development team.
< Hover by the red triangle in the top left corner for more detail. Use the Instructions on the next tab to fill out fields.>
Defect No. | Date Created | Created By | Defect Description | PM Process | Lifecycle Phase | Priority | Owner | Assigned Date | Estimated Time to Fix | Status | Resolution | Resolution Date | Actual Time to Fix | Root Cause | Status | Priority | PM | Lifecycle Phase
1 | 2026-01-02 | Edo Smola | 1. Open BMI Calculator (https://www.calculator.net/bmi-calculator.html) 2. Calculate a value for anything. 3. Upon calculation, the query string parameters will change. 4. Change the csex query parameter from "m" or "f" into any other non-gender letter (e.g. "g"). 5. Press ENTER to open the page. Upon opening, no gender will be selected, but if you click on "Calculate", it will still manage to calculate and the calculation will consider the "male" gender as default. EXPECTED RESULT: The gender radio buttons should have "Male" selected by default. An invalid query string value for csex should not be able to break the UI selection. |  | Development | Low |  |  |  | New |  |  |  |  | New
2 | 2026-01-03 | Arman Ossi Loko | 1. Go to https://gamebanana.com/contests and make sure you're logged in 2. Open any contest that has finished (usually, any older than 4 months) - e.g. https://gamebanana.com/contests/133 3. There is a "Join contest" button visible on the right side. The contest has ended over a year ago. EXPECTED RESULT: There should be no "Join contest" button because the given contest has finished over 2 years ago. |  | Development | Low |  |  |  | New |  |  |  |  | Under Review | High | Opportunity Assessment | Opportunity Assessment
3 | 2026-01-03 | Arman Ossi Loko | 1. Open gamebanana.com 2. Click on any mod for the game Left 4 Dead 2 3. There is no "Install with ModBoy" button. ModBoy is GameBanana's internally built "mod installation" tool (https://gamebanana.com/tools/6321). It has been integrated into the web application for years. EXPECTED RESULT: All Source engine games (like Left 4 Dead 2, Counter-Strike Source, etc.) support ModBoy, so all mods for the given games should have an "Install with ModBoy" button. |  | Development | Medium |  |  |  | New |  |  |  |  | In Progress | Medium | Initiating | Concept
4 | 2026-01-04 | Arman Ossi Loko | 1. Open gamebanana.com 2. Log into your account 3. Open any random profile of another person. 4. Click on the "Control Center" button below their username. Luckily, opening any specific settings page does not work. EXPECTED RESULT: Users should not be able to open the control center of other users of the site. The button should not be visible at all. |  | Development | Low |  |  |  | New |  |  |  |  | Completed | Low | Planning | Requirements
5 | 2026-01-04 | Mahir Keran | 1. Open gamebanana.com 2. Log into your account 3. Open your profile. 4. Find and click on the "Contacts" button. 5. Drag and drop YouTube from the left sidemenu and paste a YouTube link. 6. Save. 7. On your profile, the link you pasted is not clickable. It's just normal text. EXPECTED RESULT: The YouTube link should be clickable. |  | Development | Low |  |  |  | New | [6 empty] | Executing/Controlling | Design
6 | 2026-01-05 | Mahir Keran | 1. Open gamebanana.com 2. Log into your account 3. Open your profile. 4. Find and click on the "Contacts" button. 5. Drag and drop YouTube from the left sidemenu and write any text in it. 6. Save. EXPECTED RESULT: It should not be possible to save any random text as a YouTube profile link. An example of this in action and abused by an user is here: https://gamebanana.com/members/2048161 |  | Development | Low |  |  |  | New | [6 empty] | Closing | Development
7 | [17 empty] | Testing
8 | [17 empty] | Documentation and Training
9 | [17 empty] | Deployment
10 | [17 empty] | Post-Deployment
11
12
13
14
15
16
17
18
Note on E10: ====== ID#AAAAn_rmfi0 Julie Arnold (2023-01-09 19:26:29) Choose from the drop down box.
Note on F10: ====== ID#AAAAn_rmfiw John Casey (2023-01-09 19:26:29) Choose from the drop down box.
Note on G10: ====== ID#AAAAn_rmfio Julie Arnold (2023-01-09 19:26:29) Choose from the drop down list
Note on K10: ====== ID#AAAAn_rmfis Julie Arnold (2023-01-09 19:26:29) Choose from the drop down list.

## Defect Tracking Log Instruc
Defect Tracking Log Instructions
Field | Description
Defect Number | Unique identifier for the defect, i.e., 1,2 etc.
Date Created | Date on which the defect was initially reported and logged.
Created By | Name of the person who reported the defect.
Defect Description | Description of the defect. State the subsystem, area, or other part of the product in which the defect occurs or which is affected by the defect.
PM Process | Choose the Project Management Process this defect was reported for: Opportunity Assessment, Initiating, Planning, Executing/Controlling and Closing.
Lifecycle Phase | List the lifecycle this defect was reported for. The Software Development lifecycle is: Opportunity Assessment, Concept, Requirements, Design, Development, Testing, Documentation and Training, Deployment and Post Deployment.
Priority | The priority code indicates the impact of this defect on the project:
H = High (extremely important, the project cannot be successful without this defect being resolved)
M = Medium (important to project success, but a work around exists)
L = Low (desirable, but with little impact to project success if the defect is not resolved)
Owner | Name of the person who is responsible for fixing the defect.
Assigned Date | Date on which the defect was assigned for resolution.
Estimated Time To Fix | Estimated amount of time required to correct the defect. If applicable list in hours, not days.
Status | Current status of the defect: New, In Progress, Under Review and Completed.
Resolution | Description of the defect’s resolution.
Resolution Date | Date on which the defect is to be resolved (or is resolved depending upon its status).
Actual Time to Fix | Actual time required to correct the defect.
Root Cause Description | State the cause of the defect (for example, communication, oversight, transcription, education, process, bad code.).